## 26 Aug 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-08-26 |  | 2017-07-24 |  | 2017-07-15 |  | 2017-04-15 |  | 2017-03-30 |  | 2017-03-20 |  | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, wired half wa as overlap |  |  | 13 | H |  | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 0 | 3 | 0 | 3 | 0 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | All bases in place, mostly with masts, no wires |  |  | 64 | I |  | 18 | 48 | 18 | 48 | 18 | 48 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | Many bases in place, some with masts, no wires |  |  | 20 | K |  | 0 | 2 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Many bases in place, some with masts, no wires |  |  | 228 | K |  | 40 | 19 | 40 | 19 | 40 | 19 | 46 | 0 | 46 | 0 | 44 | 0 | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | All bases in place, no masts, no wires |  |  | 6 | L |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | Some bases in place, no masts, no wires. |  |  | 234 | M |  | 42 | 0 | 42 | 0 | 41 | 0 | 26 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | All bases in place, no masts, no wires |  |  | 6 | L |  | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Some bases in place, no masts, no wires. |  |  | 48 | M |  | 15 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | All bases in place, no masts, no wires |  |  | 6 | I |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases, some masts |  |  | 49 | K |  | 9 | 13 | 9 | 13 | 8 | 13 | 4 | 8 | 4 | 7 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | Fully masted, no wires |  |  | 6 | H |  | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Bolton Station | Many bases, some masts |  |  | 19 | K |  | 2 | 56 | 2 | 56 | 1 | 56 | 7 | 42 | 55 | 4 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Many bases, some masts |  |  | 133 | K |  | 9 | 0 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 140 | 155 | 140 | 155 | 137 | 143 | 122 | 53 | 154 | 13 | 129 | 2 | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Many bases, some masts |  |  | 198 | K |  | 60 | 35 | 60 | 35 | 60 | 35 | 86 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | All bases in place, mostly with masts, no wires |  |  | 152 | I |  | 27 | 65 | 27 | 65 | 27 | 65 | 37 | 43 | 37 | 43 | 37 | 43 | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | All bases in place, mostly with masts, no wires |  |  | 118 | I |  | 19 | 47 | 19 | 47 | 19 | 47 | 51 | 11 | 51 | 11 | 62 | 0 | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | All bases in place, mostly with masts, no wires |  |  | 155 | I |  | 15 | 61 | 15 | 61 | 15 | 61 | 62 | 5 | 62 | 5 | 62 | 5 | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Many bases, some masts |  |  | 239 | K |  | 55 | 47 | 55 | 47 | 55 | 47 | 112 | 0 | 112 | 0 | 112 | 0 | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Many bases, some masts |  |  | 173 | K |  | 42 | 19 | 42 | 19 | 42 | 19 | 71 | 0 | 71 | 0 | 63 | 0 | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | All bases in place, mostly with masts, no wires |  |  | 69 | I |  | 6 | 48 | 6 | 48 | 6 | 48 | 55 | 0 | 55 | 0 | 55 | 0 | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 228 | 322 | 228 | 322 | 228 | 322 | 477 | 59 | 471 | 59 | 474 | 48 | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Many bases, some masts |  |  | 348 | K |  | 159 | 67 | 111 | 57 | 111 | 57 | 138 | 0 | 138 | 0 | 138 | 0 | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | All bases in place, no masts, no wires |  |  | 6 | L |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | All bases in place, no masts, no wires |  |  | 175 | L |  | 98 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Many bases, some masts |  |  | 466 | K |  | 183 | 61 | 115 | 72 | 115 | 72 | 21 | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | Some bases in place, no masts, no wires. |  |  | 149 | M |  | 58 | 0 | 47 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | Some bases in place, no masts, no wires. |  |  | 94 | M |  | 20 | 0 | 19 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 526 | 128 | 293 | 129 | 293 | 129 | 159 | 0 | 159 | 0 | 159 | 0 | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | All bases in place, approx half with masts, no wires |  |  | 139 | J |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 919 | 605 | 686 | 606 | 683 | 594 | 783 | 112 | 809 | 72 | 787 | 50 | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on Network Rail video concerning Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1477 | 1477 | 1477 | 1477 | 1477 | 1477 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 25.86% | 32.3% | 25.86% | 32.3% | 25.66% | 31.48% | 43.79% | 8% | 45.64% | 5.143% | 44.07% | 3.571% | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-08-26 | Change | 2017-07-24 | Change | 2017-07-15 | Change | 2017-04-15 | Change | 2017-03-30 | Change | 2017-03-20 | Change | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.91% | 0% | 10.91% | 0% | 10.91% | 0% | 10.91% | 0% | 10.91% | 0.5985% | 10.91% | 0% | 10.91% | 0% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-7 |  |  | 35 | D |  | 0.7778% | 0% | 0.7778% | 0% | 0.7778% | -0.04266% | 0.8204% | 0% | 0.8204% | 0.04266% | 0.7778% | 0% | 0.7778% | 0% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 19 | H |  | 0.4222% | 0% | 0.4222% | 0% | 0.4222% | 0.1175% | 0.3047% | 0% | 0.3047% | 0.01585% | 0.2889% | 0% | 0.2889% | 0% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 564 | I |  | 12.53% | 0% | 12.53% | 0% | 12.53% | 12.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 139 | J |  | 3.089% | 0% | 3.089% | 0% | 3.089% | 3.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 1879 | K |  | 41.76% | 0% | 41.76% | 0% | 41.76% | 26.8% | 14.96% | 0% | 14.96% | 4.911% | 10.04% | 3.089% | 6.956% | 0% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 193 | L |  | 4.289% | 4.022% | 0.2667% | 0% | 0.2667% | -1.351% | 1.617% | 0% | 1.617% | 0.08411% | 1.533% | 1.533% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 692 | M |  | 15.38% | 0.1333% | 15.24% | 0% | 15.24% | -29.08% | 44.33% | 0.4688% | 43.86% | -1.853% | 45.71% | -4.067% | 49.78% | 0% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 488 | Z |  | 10.84% | -4.156% | 15% | 0% | 15% | -11.47% | 26.47% | -0.4688% | 26.93% | -3.799% | 30.73% | -0.5556% | 31.29% | 0% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4500 |  |  | 100% |  | 100% |  | 100% |  | 99.4% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 24 Jul 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-07-24 |  | 2017-07-15 |  | 2017-04-15 |  | 2017-03-30 |  | 2017-03-20 |  | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, wired half wa as overlap |  |  | 13 | H |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 0 | 3 | 0 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | All bases in place, mostly with masts, no wires |  |  | 64 | I |  | 18 | 48 | 18 | 48 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | Many bases in place, some with masts, no wires |  |  | 20 | K |  | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Many bases in place, some with masts, no wires |  |  | 228 | K |  | 40 | 19 | 40 | 19 | 46 | 0 | 46 | 0 | 44 | 0 | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | All bases in place, no masts, no wires |  |  | 6 | L |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | Some bases in place, no masts, no wires. |  |  | 234 | M |  | 42 | 0 | 41 | 0 | 26 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | All bases in place, no masts, no wires |  |  | 6 | L |  | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Some bases in place, no masts, no wires. |  |  | 48 | M |  | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | All bases in place, no masts, no wires |  |  | 6 | I |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases, some masts |  |  | 49 | K |  | 9 | 13 | 8 | 13 | 4 | 8 | 4 | 7 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | Fully masted, no wires |  |  | 6 | H |  | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Bolton Station | Many bases, some masts |  |  | 19 | K |  | 2 | 56 | 1 | 56 | 7 | 42 | 55 | 4 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Many bases, some masts |  |  | 133 | K |  | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 140 | 155 | 137 | 143 | 122 | 53 | 154 | 13 | 129 | 2 | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Many bases, some masts |  |  | 198 | K |  | 60 | 35 | 60 | 35 | 86 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | All bases in place, mostly with masts, no wires |  |  | 152 | I |  | 27 | 65 | 27 | 65 | 37 | 43 | 37 | 43 | 37 | 43 | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | All bases in place, mostly with masts, no wires |  |  | 118 | I |  | 19 | 47 | 19 | 47 | 51 | 11 | 51 | 11 | 62 | 0 | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | All bases in place, mostly with masts, no wires |  |  | 155 | I |  | 15 | 61 | 15 | 61 | 62 | 5 | 62 | 5 | 62 | 5 | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Many bases, some masts |  |  | 239 | K |  | 55 | 47 | 55 | 47 | 112 | 0 | 112 | 0 | 112 | 0 | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Many bases, some masts |  |  | 173 | K |  | 42 | 19 | 42 | 19 | 71 | 0 | 71 | 0 | 63 | 0 | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | All bases in place, mostly with masts, no wires |  |  | 69 | I |  | 6 | 48 | 6 | 48 | 55 | 0 | 55 | 0 | 55 | 0 | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 228 | 322 | 228 | 322 | 477 | 59 | 471 | 59 | 474 | 48 | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Many bases, some masts |  |  | 348 | K |  | 111 | 57 | 111 | 57 | 138 | 0 | 138 | 0 | 138 | 0 | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Many bases, some masts |  |  | 466 | K |  | 115 | 72 | 115 | 72 | 21 | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | Some bases in place, no masts, no wires. |  |  | 149 | M |  | 47 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | Some bases in place, no masts, no wires. |  |  | 94 | M |  | 19 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 293 | 129 | 293 | 129 | 159 | 0 | 159 | 0 | 159 | 0 | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | All bases in place, approx half with masts, no wires |  |  | 139 | J |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 686 | 606 | 683 | 594 | 783 | 112 | 809 | 72 | 787 | 50 | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on Network Rail video concerning Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1477 | 1477 | 1477 | 1477 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 25.86% | 32.3% | 25.66% | 31.48% | 43.79% | 8% | 45.64% | 5.143% | 44.07% | 3.571% | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-07-24 | Change | 2017-07-15 | Change | 2017-04-15 | Change | 2017-03-30 | Change | 2017-03-20 | Change | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.91% | 0% | 10.91% | 0% | 10.91% | 0% | 10.91% | 0.5985% | 10.91% | 0% | 10.91% | 0% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7778% | 0% | 0.7778% | -0.04266% | 0.8204% | 0% | 0.8204% | 0.04266% | 0.7778% | 0% | 0.7778% | 0% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 19 | H |  | 0.4222% | 0% | 0.4222% | 0.1175% | 0.3047% | 0% | 0.3047% | 0.01585% | 0.2889% | 0% | 0.2889% | 0% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 564 | I |  | 12.53% | 0% | 12.53% | 12.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 139 | J |  | 3.089% | 0% | 3.089% | 3.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 1879 | K |  | 41.76% | 0% | 41.76% | 26.8% | 14.96% | 0% | 14.96% | 4.911% | 10.04% | 3.089% | 6.956% | 0% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 12 | L |  | 0.2667% | 0% | 0.2667% | -1.351% | 1.617% | 0% | 1.617% | 0.08411% | 1.533% | 1.533% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 686 | M |  | 15.24% | 0% | 15.24% | -29.08% | 44.33% | 0.4688% | 43.86% | -1.853% | 45.71% | -4.067% | 49.78% | 0% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 675 | Z |  | 15% | 0% | 15% | -11.47% | 26.47% | -0.4688% | 26.93% | -3.799% | 30.73% | -0.5556% | 31.29% | 0% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4500 |  |  | 100% |  | 100% |  | 99.4% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 15 Jul 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-04-15 |  | 2017-04-15 |  | 2017-03-30 |  | 2017-03-20 |  | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 0 | 3 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | All bases in place, mostly with masts, no wires |  |  | 64 | I |  | 18 | 48 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | Many bases in place, some with masts, no wires |  |  | 20 | K |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Many bases in place, some with masts, no wires |  |  | 228 | K |  | 40 | 19 | 46 | 0 | 46 | 0 | 44 | 0 | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | All bases in place, no masts, no wires |  |  | 6 | L |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | Some bases in place, no masts, no wires. |  |  | 234 | M |  | 41 | 0 | 26 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | All bases in place, no masts, no wires |  |  | 6 | L |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Some bases in place, no masts, no wires. |  |  | 48 | M |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | All bases in place, no masts, no wires |  |  | 6 | I |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases, some masts |  |  | 49 | K |  | 8 | 13 | 4 | 8 | 4 | 7 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | Fully masted, no wires |  |  | 6 | H |  | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Bolton Station | Many bases, some masts |  |  | 19 | K |  | 1 | 56 | 7 | 42 | 55 | 4 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Many bases, some masts |  |  | 133 | K |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 137 | 143 | 122 | 53 | 154 | 13 | 129 | 2 | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Many bases, some masts |  |  | 198 | K |  | 60 | 35 | 86 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | All bases in place, mostly with masts, no wires |  |  | 152 | I |  | 27 | 65 | 37 | 43 | 37 | 43 | 37 | 43 | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | All bases in place, mostly with masts, no wires |  |  | 118 | I |  | 19 | 47 | 51 | 11 | 51 | 11 | 62 | 0 | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | All bases in place, mostly with masts, no wires |  |  | 155 | I |  | 15 | 61 | 62 | 5 | 62 | 5 | 62 | 5 | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Many bases, some masts |  |  | 239 | K |  | 55 | 47 | 112 | 0 | 112 | 0 | 112 | 0 | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Many bases, some masts |  |  | 173 | K |  | 42 | 19 | 71 | 0 | 71 | 0 | 63 | 0 | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | All bases in place, mostly with masts, no wires |  |  | 69 | I |  | 6 | 48 | 55 | 0 | 55 | 0 | 55 | 0 | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 228 | 322 | 477 | 59 | 471 | 59 | 474 | 48 | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Many bases, some masts |  |  | 348 | K |  | 111 | 57 | 138 | 0 | 138 | 0 | 138 | 0 | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Many bases, some masts |  |  | 466 | K |  | 115 | 72 | 21 | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | Some bases in place, no masts, no wires. |  |  | 149 | M |  | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | Some bases in place, no masts, no wires. |  |  | 94 | M |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 293 | 129 | 159 | 0 | 159 | 0 | 159 | 0 | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | All bases in place, approx half with masts, no wires |  |  | 139 | J |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 683 | 594 | 783 | 112 | 809 | 72 | 787 | 50 | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on Network Rail video concerning Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1477 | 1477 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 25.66% | 31.48% | 43.79% | 8% | 45.64% | 5.143% | 44.07% | 3.571% | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-07-15 | Change | 2017-04-15 | Change | 2017-03-30 | Change | 2017-03-20 | Change | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.91% | 0% | 10.91% | 0% | 10.91% | 0.5985% | 10.91% | 0% | 10.91% | 0% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7778% | -0.04266% | 0.8204% | 0% | 0.8204% | 0.04266% | 0.7778% | 0% | 0.7778% | 0% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 19 | H |  | 0.4222% | 0.1175% | 0.3047% | 0% | 0.3047% | 0.01585% | 0.2889% | 0% | 0.2889% | 0% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 564 | I |  | 12.53% | 12.53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 139 | J |  | 3.089% | 3.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 1879 | K |  | 41.76% | 26.8% | 14.96% | 0% | 14.96% | 4.911% | 10.04% | 3.089% | 6.956% | 0% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 12 | L |  | 0.2667% | -1.351% | 1.617% | 0% | 1.617% | 0.08411% | 1.533% | 1.533% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 686 | M |  | 15.24% | -29.08% | 44.33% | 0.4688% | 43.86% | -1.853% | 45.71% | -4.067% | 49.78% | 0% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 675 | Z |  | 15% | -11.47% | 26.47% | -0.4688% | 26.93% | -3.799% | 30.73% | -0.5556% | 31.29% | 0% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4500 |  |  | 100% |  | 99.4% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 15 Apr 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-04-15 |  | 2017-03-30 |  | 2017-03-20 |  | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | Some bases in place, no masts, no wires. |  |  | 20 | M |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 46 | 0 | 46 | 0 | 44 | 0 | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | Some bases in place, no masts, no wires. |  |  | 234 | N |  | 26 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works completed |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases, some masts |  |  | 49 | K |  | 4 | 8 | 4 | 7 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station south end to Bolton Station | Many bases, some masts |  |  | 19 | K |  | 7 | 42 | 55 | 4 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Major works planned during 2017 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 122 | 53 | 154 | 13 | 129 | 2 | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Some bases in place, no masts, no wires. |  |  | 198 | M |  | 86 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Many bases, some masts |  |  | 152 | K |  | 37 | 43 | 37 | 43 | 37 | 43 | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Many bases, some masts |  |  | 118 | K |  | 51 | 11 | 51 | 11 | 62 | 0 | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Many bases, some masts |  |  | 155 | K |  | 62 | 5 | 62 | 5 | 62 | 5 | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 112 | 0 | 112 | 0 | 112 | 0 | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 71 | 0 | 71 | 0 | 63 | 0 | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | L |  | 55 | 0 | 55 | 0 | 55 | 0 | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 477 | 59 | 471 | 59 | 474 | 48 | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Some bases in place, no masts, no wires. |  |  | 348 | M |  | 138 | 0 | 138 | 0 | 138 | 0 | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Some bases in place, no masts, no wires. |  |  | 466 | M |  | 21 | 0 | 21 | 0 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 159 | 0 | 159 | 0 | 159 | 0 | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Many bases in place, some with masts, no wires |  |  | 139 | K |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 783 | 112 | 809 | 72 | 787 | 50 | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 43.79% | 8% | 45.64% | 5.143% | 44.07% | 3.571% | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-03-30 | Change | 2017-03-30 | Change | 2017-03-20 | Change | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 11.51% | 0% | 11.51% | 0.5985% | 10.91% | 0% | 10.91% | 0% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.8204% | 0% | 0.8204% | 0.04266% | 0.7778% | 0% | 0.7778% | 0% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.3047% | 0% | 0.3047% | 0.01585% | 0.2889% | 0% | 0.2889% | 0% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 638 | K |  | 14.96% | 0% | 14.96% | 4.911% | 10.04% | 3.089% | 6.956% | 0% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 69 | L |  | 1.617% | 0% | 1.617% | 0.08411% | 1.533% | 1.533% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1891 | M |  | 44.33% | 0.4688% | 43.86% | -1.853% | 45.71% | -4.067% | 49.78% | 0% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 1129 | Z |  | 26.47% | -0.4688% | 26.93% | -3.799% | 30.73% | -0.5556% | 31.29% | 0% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4266 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 30 Mar 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-03-30 |  | 2017-03-20 |  | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 46 | 0 | 44 | 0 | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | Some bases in place, no masts, no wires. |  |  | 234 | N |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works completed |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases, some masts |  |  | 49 | K |  | 4 | 7 | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station south end to Bolton Station | Many bases, some masts |  |  | 19 | K |  | 55 | 4 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Major works planned during 2017 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 154 | 13 | 129 | 2 | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Some bases in place, no masts, no wires. |  |  | 198 | M |  | 80 | 0 | 80 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Many bases, some masts |  |  | 152 | K |  | 37 | 43 | 37 | 43 | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Many bases, some masts |  |  | 118 | K |  | 51 | 11 | 62 | 0 | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Many bases, some masts |  |  | 155 | K |  | 62 | 5 | 62 | 5 | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 112 | 0 | 112 | 0 | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 71 | 0 | 63 | 0 | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | L |  | 55 | 0 | 55 | 0 | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 471 | 59 | 474 | 48 | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Some bases in place, no masts, no wires. |  |  | 348 | M |  | 138 | 0 | 138 | 0 | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Some bases in place, no masts, no wires. |  |  | 466 | M |  | 21 | 0 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 159 | 0 | 159 | 0 | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Many bases in place, some with masts, no wires |  |  | 139 | K |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 809 | 72 | 787 | 50 | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 45.64% | 5.143% | 44.07% | 3.571% | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-03-30 | Change | 2017-03-20 | Change | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 11.51% | 0.5985% | 10.91% | 0% | 10.91% | 0% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.8204% | 0.04266% | 0.7778% | 0% | 0.7778% | 0% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.3047% | 0.01585% | 0.2889% | 0% | 0.2889% | 0% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 638 | K |  | 14.96% | 4.911% | 10.04% | 3.089% | 6.956% | 0% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 69 | L |  | 1.617% | 0.08411% | 1.533% | 1.533% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1871 | M |  | 43.86% | -1.853% | 45.71% | -4.067% | 49.78% | 0% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 1149 | Z |  | 26.93% | -3.799% | 30.73% | -0.5556% | 31.29% | 0% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4266 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 20 Mar 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-03-20 |  | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 1 | 2 | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 44 | 0 | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases in place, no masts, no wires. |  |  | 49 | M |  | 11 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station south end to Bolton Station | Some bases in place, no masts, no wires. |  |  | 19 | M |  | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Major works planned during 2017 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 129 | 2 | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Some bases in place, no masts, no wires. |  |  | 198 | M |  | 80 | 0 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Many bases, some masts |  |  | 152 | K |  | 37 | 43 | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 62 | 0 | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Many bases, some masts |  |  | 155 | K |  | 62 | 5 | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 112 | 0 | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 63 | 0 | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | L |  | 55 | 0 | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 474 | 48 | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Some bases in place, no masts, no wires. |  |  | 348 | M |  | 138 | 0 | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Some bases in place, no masts, no wires. |  |  | 466 | M |  | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 159 | 0 | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Many bases in place, some with masts, no wires |  |  | 139 | K |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 787 | 50 | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 44.07% | 3.571% | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-03-20 | Change | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.91% | 0% | 10.91% | 0% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7778% | 0% | 0.7778% | 0% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2889% | 0% | 0.2889% | 0% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 452 | K |  | 10.04% | 3.089% | 6.956% | 0% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 69 | L |  | 1.533% | 1.533% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 2057 | M |  | 45.71% | -4.067% | 49.78% | 0% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 1383 | Z |  | 30.73% | -0.5556% | 31.29% | 0% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4500 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 9 Mar 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-03-09 |  | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 1 | 2 | 1 | 2 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 44 | 0 | 25 | 0 | 28 | 0 | 22 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Farnworth Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Farnworth station north end to Moses Gate station south end | Some bases in place, no masts, no wires. |  |  | 49 | M |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station south end to Bolton Station | No bases, masts or wires |  |  | 19 | Z |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Bolton station | Major works planned during 2015-17 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 122 | 2 | 63 | 2 | 65 | 0 | 59 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bolton station N end to Lostock station S end | Some bases in place, no masts, no wires. |  |  | 198 | M |  | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Many bases, some masts |  |  | 152 | K |  | 61 | 22 | 61 | 22 | 50 | 21 | 86 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 62 | 0 | 62 | 0 | 47 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Many bases, some masts |  |  | 155 | K |  | 62 | 5 | 60 | 5 | 34 | 5 | 89 | 4
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 104 | 0 | 102 | 0 | 57 | 0 | 116 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 63 | 0 | 53 | 0 | 43 | 0 | 24 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | M |  | 54 | 0 | 51 | 0 | 9 | 0 | 4 | 0
[7 empty] | Totals | 489 | 27 | 472 | 27 | 243 | 26 | 362 | 4
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Some bases in place, no masts, no wires. |  |  | 348 | M |  | 96 | 0 | 39 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | Some bases in place, no masts, no wires. |  |  | 466 | M |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3847 |  | Totals | 117 | 0 | 39 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 11 | 0 | 8 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Some bases in place, no masts, no wires. |  |  | 139 | M |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0
|  |  | Totals |  | 4500 |  | Totals | 753 | 29 | 596 | 29 | 322 | 26 | 435 | 4
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 44.64% | 2.071% | 39.21% | 2.071% | 23% | 1.857% | 31.07% | 0.2857%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-03-09 | Change | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.91% | 0.02419% | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7778% | 0.001725% | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2889% | 0.0006406% | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 313 | K |  | 6.956% | 0.01542% | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 2240 | M |  | 49.78% | 11.53% | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133%
| Z | No bases, masts or wires |  |  | 1408 | Z |  | 31.29% | -11.57% | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133%
|  |  |  | Overall | 4500 |  |  | 100% |  | 100% |  | 100% |  | 100%

## 16 Feb 2017
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2017-02-16 |  | 2016-10-25 |  | 2016-04-18 |  | 2016-04-13 |  | 2016-04-07 |  | 2016-01-14 |  | 2015-05-11 |  | 2015-04-08 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 6 | K |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 25 | 0 | 28 | 0 | 22 | 0 | 22 | 0 | 22 | 0 | 11 | 0 | 20 | 0 | 0 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015-17 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 63 | 2 | 65 | 0 | 59 | 0 | 59 | 0 | 59 | 0 | 57 | 0 | 57 | 0 | 30 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | Some bases in place, no masts, no wires. |  |  | 198 | M |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Many bases, some masts |  |  | 152 | K |  | 57 | 20 | 50 | 21 | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 68 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 62 | 0 | 47 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Many bases, some masts |  |  | 155 | K |  | 60 | 5 | 34 | 5 | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 0 | 84 | 0 | 84 | 0
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 102 | 0 | 57 | 0 | 116 | 0 | 116 | 0 | 116 | 0 | 85 | 0 | 85 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 53 | 0 | 43 | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | M |  | 51 | 0 | 9 | 0 | 4 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 468 | 25 | 243 | 26 | 362 | 4 | 362 | 4 | 357 | 4 | 301 | 4 | 301 | 0 | 254 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | Some bases in place, no masts, no wires. |  |  | 348 | M |  | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3857 |  | Totals | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | Some bases in place, no masts, no wires. |  |  | 143 | M |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Some bases in place, no masts, no wires. |  |  | 139 | M |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | Totals | 592 | 27 | 322 | 26 | 435 | 4 | 435 | 4 | 430 | 4 | 358 | 4 | 358 | 0 | 284 | 0 | 284 | 0
[23 empty] | ` |  | `
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 38.93% | 1.929% | 23% | 1.857% | 31.07% | 0.2857% | 31.07% | 0.2857% | 30.71% | 0.2857% | 25.57% | 0.2857% | 25.57% | 0% | 20.29% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2017-02-16 | Change | 2016-10-25 | Change | 2016-04-18 | Change | 2016-04-13 | Change | 2016-04-07 | Change | 2016-01-14 | Change | 2015-04-20 | Change | 2015-03-30 | Change | 2015-03-30 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.89% | -3.991e-08% | 10.89% | 3.991e-08% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7761% | 1.508e-08% | 0.7761% | -1.508e-08% | 0.7761% | 0% | 0.7761% | 0% | 0.7761% | 0.7761% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -0.5987% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2882% | 3.703e-08% | 0.2882% | -3.703e-08% | 0.2882% | 0% | 0.2882% | 0% | 0.2882% | -0.1774% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 313 | K |  | 6.94% | 0.133% | 6.807% | 3.37% | 3.437% | 0% | 3.437% | 0% | 3.437% | 0% | 3.437% | 3.437% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1725 | M |  | 38.25% | 15.28% | 22.97% | -3.37% | 26.34% | 0.133% | 26.21% | 0% | 26.21% | 8.448% | 17.76% | -3.437% | 21.2% | 0% | 16.14% | 0% | 16.14% | 0%
| Z | No bases, masts or wires |  |  | 1933 | Z |  | 42.86% | -15.41% | 58.27% | 2.217e-08% | 58.27% | -0.133% | 58.4% | 0% | 58.4% | -8.448% | 66.85% | 0% | 66.85% | 0% | 71.91% | 0% | 71.91% | 0%
|  |  |  | Overall | 4510 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 25 Oct 2016
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2016-10-25 |  | 2016-04-18 |  | 2016-04-13 |  | 2016-04-07 |  | 2016-01-14 |  | 2015-05-11 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 28 | 0 | 22 | 0 | 22 | 0 | 22 | 0 | 11 | 0 | 20 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015-17 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 65 | 0 | 59 | 0 | 59 | 0 | 59 | 0 | 57 | 0 | 57 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Many bases, some masts |  |  | 152 | K |  | 50 | 21 | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 47 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Many bases, some masts |  |  | 155 | K |  | 34 | 5 | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 57 | 0 | 116 | 0 | 116 | 0 | 116 | 0 | 85 | 0 | 85 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 43 | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | M |  | 9 | 0 | 4 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 243 | 26 | 362 | 4 | 362 | 4 | 357 | 4 | 301 | 4 | 301 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3857 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Some bases in place, no masts, no wires. |  |  | 139 | M |  | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | Totals | 322 | 26 | 435 | 4 | 435 | 4 | 430 | 4 | 358 | 4 | 358 | 0 | 284 | 0
`
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 23% | 1.857% | 31.07% | 0.2857% | 31.07% | 0.2857% | 30.71% | 0.2857% | 25.57% | 0.2857% | 25.57% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2016-10-25 | Change | 2016-04-18 | Change | 2016-04-13 | Change | 2016-04-07 | Change | 2016-01-14 | Change | 2015-04-20 | Change | 2015-03-30 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7761% | 0% | 0.7761% | 0% | 0.7761% | 0% | 0.7761% | 0.7761% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -0.5987% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2882% | 0% | 0.2882% | 0% | 0.2882% | 0% | 0.2882% | -0.1774% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | Many bases in place, some with masts, no wires |  |  | 307 | K |  | 6.807% | 3.37% | 3.437% | 0% | 3.437% | 0% | 3.437% | 0% | 3.437% | 3.437% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1036 | M |  | 22.97% | -3.37% | 26.34% | 0.133% | 26.21% | 0% | 26.21% | 8.448% | 17.76% | -3.437% | 21.2% | 0% | 16.14% | 0%
| Z | No bases, masts or wires |  |  | 2628 | Z |  | 58.27% | 0% | 58.27% | -0.133% | 58.4% | 0% | 58.4% | -8.448% | 66.85% | 0% | 66.85% | 0% | 71.91% | 0%
|  |  |  | Overall | 4510 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 18 Apr 2016
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2016-04-18 |  | 2016-04-13 |  | 2016-04-07 |  | 2016-01-14 |  | 2015-05-11 |  | 2015-04-20 |  | 2015-04-13 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 22 | 0 | 22 | 0 | 22 | 0 | 11 | 0 | 20 | 0 | 20 | 0 | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015-17 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 59 | 0 | 59 | 0 | 59 | 0 | 57 | 0 | 57 | 0 | 57 | 0 | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Some bases in place, no masts, no wires. |  |  | 152 | M |  | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 72 | 0 | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Some bases in place, no masts, no wires. |  |  | 155 | K |  | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 0 | 89 | 0 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 116 | 0 | 116 | 0 | 116 | 0 | 85 | 0 | 85 | 0 | 62 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 24 | 0 | 24 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | Some bases in place, no masts, no wires. |  |  | 6 | M |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | M |  | 4 | 0 | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 362 | 4 | 362 | 4 | 357 | 4 | 301 | 4 | 301 | 0 | 264 | 0 | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3857 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Some bases in place, no masts, no wires. |  |  | 139 | M |  | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | Totals | 435 | 4 | 435 | 4 | 430 | 4 | 358 | 4 | 358 | 0 | 321 | 0 | 312 | 0 | 284 | 0
`
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 31.07% | 0.2857% | 31.07% | 0.2857% | 30.71% | 0.2857% | 25.57% | 0.2857% | 25.57% | 0% | 22.93% | 0% | 22.29% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2016-04-18 | Change | 2016-04-13 | Change | 2016-04-07 | Change | 2016-01-14 | Change | 2015-04-20 | Change | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7761% | 0% | 0.7761% | 0% | 0.7761% | 0.7761% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | 0% | 0% | -0.5987% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2882% | 0% | 0.2882% | 0% | 0.2882% | -0.1774% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 155 | K |  | 3.437% | 0% | 3.437% | 0% | 3.437% | 0% | 3.437% | 3.437% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1188 | M |  | 26.34% | 0.133% | 26.21% | 0% | 26.21% | 8.448% | 17.76% | -3.437% | 21.2% | 0% | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0%
| Z | No bases, masts or wires |  |  | 2628 | Z |  | 58.27% | -0.133% | 58.4% | 0% | 58.4% | -8.448% | 66.85% | 0% | 66.85% | 0% | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0%
|  |  |  | Overall | 4510 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 13 Apr 2016
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2016-04-13 |  | 2016-04-07 |  | 2016-01-14 |  | 2015-05-11 |  | 2015-04-20 |  | 2015-04-13 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 22 | 0 | 22 | 0 | 11 | 0 | 20 | 0 | 20 | 0 | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015-17 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 59 | 0 | 59 | 0 | 57 | 0 | 57 | 0 | 57 | 0 | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Some bases in place, no masts, no wires. |  |  | 152 | M |  | 86 | 0 | 86 | 0 | 86 | 0 | 86 | 0 | 72 | 0 | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Some bases in place, no masts, no wires. |  |  | 155 | K |  | 89 | 4 | 89 | 4 | 89 | 4 | 89 | 0 | 89 | 0 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 116 | 0 | 116 | 0 | 85 | 0 | 85 | 0 | 62 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 25 | 0 | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | M |  | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 362 | 4 | 357 | 4 | 301 | 4 | 301 | 0 | 264 | 0 | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3857 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Some bases in place, no masts, no wires. |  |  | 139 | M |  | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | Totals | 435 | 4 | 430 | 4 | 358 | 4 | 358 | 0 | 321 | 0 | 312 | 0 | 284 | 0
`
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 31.07% | 0.2857% | 30.71% | 0.2857% | 25.57% | 0.2857% | 25.57% | 0% | 22.93% | 0% | 22.29% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2016-04-13 | Change | 2016-04-07 | Change | 2016-01-14 | Change | 2015-04-20 | Change | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7761% | 0% | 0.7761% | 0.7761% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | 0% | 0% | -0.5987% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2882% | 0% | 0.2882% | -0.1774% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 155 | K |  | 3.437% | 0% | 3.437% | 0% | 3.437% | 3.437% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1182 | M |  | 26.21% | 0% | 26.21% | 8.448% | 17.76% | -3.437% | 21.2% | 0% | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0%
| Z | No bases, masts or wires |  |  | 2634 | Z |  | 58.4% | 0% | 58.4% | -8.448% | 66.85% | 0% | 66.85% | 0% | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0%
|  |  |  | Overall | 4510 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 7 Apr 2016
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[8 empty] | 2016-04-07 |  | 2016-01-14 |  | 2015-05-11 |  | 2015-04-20 |  | 2015-04-13 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Fully wired in 2013-5 |  |  | 27 | D
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Fully wired in 2013-5 |  |  | 8 | D
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Some bases in place, no masts, no wires. |  |  | 64 | M |  | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | Some bases in place, no masts, no wires. |  |  | 228 | M |  | 22 | 0 | 11 | 0 | 20 | 0 | 20 | 0 | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015-17 |  |  | 133 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 59 | 0 | 57 | 0 | 57 | 0 | 57 | 0 | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Some bases in place, no masts, no wires. |  |  | 152 | M |  | 86 | 0 | 86 | 0 | 86 | 0 | 72 | 0 | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Some bases in place, no masts, no wires. |  |  | 118 | M |  | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Some bases in place, no masts, no wires. |  |  | 155 | K |  | 89 | 4 | 89 | 4 | 89 | 0 | 89 | 0 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | Some bases in place, no masts, no wires. |  |  | 6 | Z |  | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Some bases in place, no masts, no wires. |  |  | 239 | M |  | 116 | 0 | 85 | 0 | 85 | 0 | 62 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | Some bases in place, no masts, no wires. |  |  | 173 | M |  | 24 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | Some bases in place, no masts, no wires. |  |  | 69 | M |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Totals | 357 | 4 | 301 | 4 | 301 | 0 | 264 | 0 | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3857 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | Totals | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status |  | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | Some bases in place, no masts, no wires. |  |  | 139 | M |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 139 |  | Totals | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | Totals | 430 | 4 | 358 | 4 | 358 | 0 | 321 | 0 | 312 | 0 | 284 | 0
`
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [7 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [7 empty] | 30.71% | 0.2857% | 25.57% | 0.2857% | 25.57% | 0% | 22.93% | 0% | 22.29% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[8 empty] | 2016-04-07 | Change | 2016-01-14 | Change | 2015-04-20 | Change | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change | 2015-03-16 | Base | 2015-03-08 | Base | 2015-03-08
| Key |  |  |  | Chains |  |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A |  | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 35 | D |  | 0.7761% | 0.7761% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 0 | E |  | 0% | -0.5987% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | F |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 13 | H |  | 0.2882% | -0.1774% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 155 | K |  | 3.437% | 0% | 3.437% | 3.437% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 1182 | M |  | 26.21% | 8.448% | 17.76% | -3.437% | 21.2% | 0% | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 2634 | Z |  | 58.4% | -8.448% | 66.85% | 0% | 66.85% | 0% | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 |  |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 14 Jan 2016
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[7 empty] | 2016-01-14 |  | 2015-05-11 |  | 2015-04-20 |  | 2015-04-13 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 8 | H
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | 31 'normal' bases plus 6 'slabs', no masts, no wires |  |  | 64 | M | 37 | 0 | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | 11 bases in place, no masts, no wires. |  |  | 228 | M | 20 | 0 | 20 | 0 | 20 | 0 | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  |  | 133 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 57 | 0 | 57 | 0 | 57 | 0 | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | 72 bases in place, no masts, no wires. |  |  | 152 | M | 86 | 0 | 86 | 0 | 72 | 0 | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | 40 bases in place, no masts, no wires. |  |  | 118 | M | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Some bases in place, plus four masts |  |  | 155 | K | 89 | 4 | 89 | 0 | 89 | 0 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | 1 base in place, no masts, no wires. |  |  | 6 | Z | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Approx 62 bases in place, no masts, no wires. |  |  | 239 | M | 85 | 0 | 85 | 0 | 62 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  |  | 173 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  |  | 69 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 301 | 4 | 301 | 0 | 264 | 0 | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 3857 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  |  | 139 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Total | 139 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | 358 | 4 | 358 | 0 | 321 | 0 | 312 | 0 | 284 | 0
`
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [6 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [6 empty] | 25.57% | 0.2857% | 25.57% | 0% | 22.93% | 0% | 22.29% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[7 empty] | 2016-01-14 | Change | 2015-05-11 | Change | 2015-04-20 | Change | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change | 2015-03-16 | Change | 2015-03-08
| Key |  |  |  | Chains |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 0 | D | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 27 | E | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 21 | H | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 155 | K | 3.437% | 3.437% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 801 | M | 17.76% | -3.437% | 21.2% | 0% | 21.2% | 0% | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 3015 | Z | 66.85% | 0% | 66.85% | 0% | 66.85% | 0% | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 11 May 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[7 empty] | 2015-05-11 |  | 2015-04-20 |  | 2015-04-13 |  | 2015-04-08
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 8 | H
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | 31 'normal' bases plus 6 'slabs', no masts, no wires |  |  | 64 | M | 37 | 0 | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | 11 bases in place, no masts, no wires. |  |  | 228 | M | 20 | 0 | 20 | 0 | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  |  | 133 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 57 | 0 | 57 | 0 | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | 72 bases in place, no masts, no wires. |  |  | 152 | M | 86 | 0 | 72 | 0 | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | 40 bases in place, no masts, no wires. |  |  | 118 | M | 40 | 0 | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | 89 bases in place, no masts, no wires. |  |  | 155 | M | 89 | 0 | 89 | 0 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | 1 base in place, no masts, no wires. |  |  | 6 | Z | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Approx 62 bases in place, no masts, no wires. |  |  | 239 | M | 85 | 0 | 62 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  |  | 173 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  |  | 69 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Mvmich
[7 empty] | 301 | 0 | 264 | 0 | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A | [14 empty] | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
|  |  |  | Total | 3857 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | Mvmich
LCN Lostock Junction to Crow Nest Junction | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) | [15 empty] | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  |  | 139 | Z | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
|  |  |  | Total | 139 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | 358 | 0 | 321 | 0 | 312 | 0 | 284 | 0
`
Target masts (also bases) based on an average of 30 per kilometre (15 pairs) for Phase 4 Deal St to Euxton Jct plus Windsor Link | [6 empty] | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400 | 1400
% achieved to date | [6 empty] | 25.57% | 0% | 22.93% | 0% | 22.29% | 0% | 20.29% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[7 empty] | 2015-04-20 | Change | 2015-04-20 | Change | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change | 2015-03-16 | Change | 2015-03-08 | Change | 2015-03-08
| Key |  |  |  | Chains |  | % |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 0 | D | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 27 | E | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 21 | H | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 0 | K | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 956 | M | 21.2% | 0% | 21.2% | 0% | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 3015 | Z | 66.85% | 0% | 66.85% | 0% | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 20 Apr 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[7 empty] | 20th April |  | 13th April |  | 8th April
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 8 | H
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H | 0 | 0 | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | 31 'normal' bases plus 6 'slabs', no masts, no wires |  |  | 64 | M | 37 | 0 | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z | 0 | 0 | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | 11 bases in place, no masts, no wires. |  |  | 228 | M | 20 | 0 | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z | 0 | 0 | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z | 0 | 0 | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z | 0 | 0 | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z | 0 | 0 | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  |  | 133 | Z | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 57 | 0 | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z | 0 | 0 | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z | 0 | 0 | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | 72 bases in place, no masts, no wires. |  |  | 152 | M | 72 | 0 | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | 40 bases in place, no masts, no wires. |  |  | 118 | M | 40 | 0 | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | 89 bases in place, no masts, no wires. |  |  | 155 | M | 89 | 0 | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | 1 base in place, no masts, no wires. |  |  | 6 | Z | 1 | 0 | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Approx 62 bases in place, no masts, no wires. |  |  | 239 | M | 62 | 0 | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  |  | 173 | Z | 0 | 0 | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  |  | 69 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Mvmich
[7 empty] | 264 | 0 | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A | [13 empty] | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | Total | 3857 |  | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Mvmich
LCN Lostock Junction to Crow Nest Junction | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z | 0 | 0 | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z | 0 | 0 | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML) | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z | 0 | 0 | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z | 0 | 0 | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z | 0 | 0 | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | 0 | 0 | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) | [14 empty] | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  |  | 139 | Z | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0
|  |  |  | Total | 139 |  | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | 321 | 0 | 312 | 0 | 284 | 0
`
| Table 2: This gives an idea of progress against an estimated total of 1230 masts needed for the scheme overall. | [5 empty] | 1230 | 1230 | 1230 | 1230 | 1230 | 1230
[7 empty] | 26.1% | 0% | 25.37% | 0% | 23.09% | 0%
Table 3: This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' columns O, Q, S…etc were suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[7 empty] | 2015-04-20 | Change | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change | 2015-03-16 | Change | 2015-03-08 | Change | 2015-03-08
| Key |  |  |  | Chains |  | % |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 0 | D | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 27 | E | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 21 | H | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 0 | K | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 956 | M | 21.2% | 0% | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 3015 | Z | 66.85% | 0% | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 13 Apr 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
[7 empty] | 13th April |  | 8th April
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 8 | H
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H | 0 | 0 | 0 | 0
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | 31 'normal' bases plus 6 'slabs', no masts, no wires |  |  | 64 | M | 37 | 0 | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z | 0 | 0 | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | 11 bases in place, no masts, no wires. |  |  | 228 | M | 11 | 0 | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z | 0 | 0 | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z | 0 | 0 | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z | 0 | 0 | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z | 0 | 0 | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  |  | 133 | Z | 0 | 0 | 0 | 0
[7 empty] | 48 | 0 | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z | 0 | 0 | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z | 0 | 0 | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | 72 bases in place, no masts, no wires. |  |  | 152 | M | 72 | 0 | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | 40 bases in place, no masts, no wires. |  |  | 118 | M | 40 | 0 | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | 89 bases in place, no masts, no wires. |  |  | 155 | M | 89 | 0 | 84 | 0
19.12-19.18 | Adlington station | 1 base in place, no masts, no wires. |  |  | 6 | Z | 1 | 0 | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Approx 62 bases in place, no masts, no wires. |  |  | 239 | M | 62 | 0 | 62 | 0
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  |  | 173 | Z | 0 | 0 | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  |  | 69 | Z | 0 | 0 | 0 | 0 | [7 empty] | MVch | Mvmiles | Mvmich
[7 empty] | 264 | 0 | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A | [11 empty] | 0 | 0 | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
|  |  |  | Total | 3857 |  | 0 | 0 | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  | 0 | 0 | 0 | 0 | [7 empty] | MVch | Mvmiles | Mvmich
LCN Lostock Junction to Crow Nest Junction | [6 empty] | 0 | 0 | 0 | 0
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z | 0 | 0 | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z | 0 | 0 | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML) | [6 empty] | 0 | 0 | 0 | 0
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z | 0 | 0 | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z | 0 | 0 | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z | 0 | 0 | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z | 0 | 0 | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  | 0 | 0 | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction ("Windsor Link") |  |  |  | Chains | Status | Bare Bases | Masts | Bare Bases | Masts
From-To |  |  |  |  | (Approx) | [12 empty] | MVch | Mvmiles | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  |  | 139 | Z | 0 | 0 | 0 | 0 | [7 empty] | 0 | 0 | 0
|  |  |  | Total | 139 |  | 0 | 0 | 0 | 0
|  |  | Totals |  | 4510 |  | 312 | 0 | 284 | 0
`
Table 2. This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' column M was suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[7 empty] | 2015-04-13 | Change | 2015-04-08 | Change | 2015-03-30 | Change | 2015-03-16 | Change | 2015-03-08 | Change | 2015-03-08
| Key |  |  |  | Chains |  | % |  | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | A | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | B | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | C | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 0 | D | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 27 | E | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | F | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | G | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 21 | H | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | I | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | J | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 0 | K | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | L | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 956 | M | 21.2% | 5.055% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 3015 | Z | 66.85% | -5.055% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 |  | 100% |  | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 8 Apr 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 8 | H
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 |  | Count needed
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Approx 30 bases in place, no masts, no wires |  |  | 64 | M |  | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | No bases, masts or wires |  |  | 228 | Z |  | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  |  | 133 | Z |  | 0 | 0
[8 empty] | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z |  | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Approx 68 bases in place, no masts, no wires. |  |  | 152 | M |  | 68 | 0
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Approx 40 bases in place, no masts, no wires. |  |  | 118 | M |  | 40 | 0
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Approx 84 bases in place, no masts, no wires. |  |  | 155 | M |  | 84 | 0
19.12-19.18 | Adlington station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Approx 62 bases in place, no masts, no wires. |  |  | 239 | M |  | 62 | 0 |  | Updated 8th Apr
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  |  | 173 | Z |  | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  |  | 69 | Z |  | 0 | 0 | [5 empty] | MVch | Mvmiles | Mvmich
[8 empty] | 254 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A | [8 empty] | 0 | 0 | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
|  |  |  | Total | 3857 |  |  | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 | [5 empty] | MVch | Mvmiles | Mvmich
LCN Lostock Junction to Crow Nest Junction | [7 empty] | 0 | 0
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z |  | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML) | [7 empty] | 0 | 0
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  |  | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction |  |  |  | Chains | Status |  | Bare Bases | Masts
From-To |  |  |  |  | (Approx) | [9 empty] | MVch | Mvmiles | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  |  | 139 | Z |  | 0 | 0 | [5 empty] | 0 | 0 | 0
|  |  |  | Total | 139 |  |  | 0 | 0
|  |  | Totals |  | 4510 |  |  | 284 | 0
`
Table 2. This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' column M was suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[6 empty] | 2015-04-08 | Change | 2015-03-30 | Change | 2015-03-16 | Change | 2015-03-08 | Change | 2015-03-08
| Key |  |  |  | Chains | % |  | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 27 | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 21 | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 728 | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 3243 | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 | 100% |  | 100% |  | 100% |  | 100% |  | 100%

## 30 Mar 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
m.ch | Manchester Victoria to Blackpool |  |  |  | Chains | Status |  | Bare Bases | Masts
From-To |  |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  |  | 8 | H
Phase 4, Deal St Junction to Blackpool North
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  |  | 13 | H |  | 0 | 0 |  | Count needed
0.56-0.62 | Salford Central | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Approx 30 bases in place, no masts, no wires |  |  | 64 | M |  | 30 | 0
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  |  | 20 | Z |  | 0 | 0
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | No bases, masts or wires |  |  | 228 | Z |  | 0 | 0
4.54-4.60 | Clifton Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  |  | 234 | Z |  | 0 | 0
7.54-7.60 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  |  | 48 | Z |  | 0 | 0
8.28-8.34 | Kearsley Station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  |  | 49 | Z |  | 0 | 0
9.03-9.09 | Moses Gate station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  |  | 19 | Z |  | 0 | 0
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  |  | 133 | Z |  | 0 | 0
[8 empty] | 30 | 0
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  |  | 198 | Z |  | 0 | 0
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  |  | 10 | Z |  | 0 | 0
13.49-13.55 | Lostock station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Approx 68 bases in place, no masts, no wires. |  |  | 152 | M |  | 68 | 0 |  | Updated 30th Mar
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Approx 40 bases in place, no masts, no wires. |  |  | 118 | M |  | 40 | 0 |  | Updated 30th Mar
17.11-17.17 | Blackrod station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
17.17-19.12 | Blackrod station north end to Adlington station south end | Approx 84 bases in place, no masts, no wires. |  |  | 155 | M |  | 84 | 0 |  | Updated 30th Mar
19.12-19.18 | Adlington station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
19.18-22.17 | Adlington station north end to Chorley station south end | Approx 52 bases in place, no masts, no wires. |  |  | 239 | M |  | 52 | 0 |  | Updated 30th Mar
22.17-22.23 | Chorley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  |  | 173 | Z |  | 0 | 0
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  |  | 69 | Z |  | 0 | 0 |  |  |  | MVch | Mvmiles | Mvmich
[8 empty] | 244 | 0
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  |  | 491 | A | [6 empty] | 0 | 0 | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  |  | 348 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  |  | 175 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  |  | 87 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  |  | 466 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  |  | 12 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  |  | 149 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  |  | 94 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | Total | 3857 |  |  | 0 | 0
m.ch | Lostock Junction to Wigan North Western |  |  |  | Chains | Status |  | Bare Bases | Masts
From-To |  |  |  |  | (Approx) |  |  | 0 | 0 |  |  |  | MVch | Mvmiles | Mvmich
LCN Lostock Junction to Crow Nest Junction | [7 empty] | 0 | 0
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  |  | 143 | Z |  | 0 | 0
1.63-1.69 | Westhoughton station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  |  | 150 | Z |  | 0 | 0
WBS2 Crow Nest Junction to Wigan North Western (WCML) | [7 empty] | 0 | 0
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  |  | 30 | Z |  | 0 | 0
4.09-4.15 | Hindley station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  |  | 123 | Z |  | 0 | 0
5.58-5.64 | Ince station | No bases, masts or wires |  |  | 6 | Z |  | 0 | 0
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  |  | 50 | Z |  | 0 | 0
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  |  | A
|  |  |  | Total | 514 |  |  | 0 | 0
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction |  |  |  | Chains | Status |  | Bare Bases | Masts
From-To |  |  |  |  | (Approx) | [7 empty] | MVch | Mvmiles | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  |  | 139 | Z |  | 0 | 0 |  |  |  | 0 | 0 | 0
|  |  |  | Total | 139 |  |  | 0 | 0
|  |  | Totals |  | 4510 |  |  | 274 | 0
`
Table 2. This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' column M was suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[6 empty] | 2015-03-30 | Change | 2015-03-16 | Change | 2015-03-08 | Change | 2015-03-08
| Key |  |  |  | Chains | % |  | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  |  | 491 | 10.89% | 0% | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  |  | 27 | 0.5987% | 0% | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  |  | 21 | 0.4656% | 0% | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  |  | 0 | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  |  | 728 | 16.14% | 0% | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  |  | 3243 | 71.91% | 0% | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  |  | Overall | 4510 | 100% |  | 100% |  | 100% |  | 100%

## 16 Mar 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
m.ch | Manchester Victoria to Blackpool |  |  | Chains | Status
From-To |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  | 8 | H
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  | 13 | H
0.56-0.62 | Salford Central | No bases, masts or wires |  | 6 | Z
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | Approx 30 bases in place, no masts, no wires |  | 64 | M |  | Updated 16th March
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  | 20 | Z
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | No bases, masts or wires |  | 228 | Z
4.54-4.60 | Clifton Station | No bases, masts or wires |  | 6 | Z
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  | 234 | Z
7.54-7.60 | Kearsley Station | No bases, masts or wires |  | 6 | Z
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  | 48 | Z
8.28-8.34 | Kearsley Station | No bases, masts or wires |  | 6 | Z
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  | 49 | Z
9.03-9.09 | Moses Gate station | No bases, masts or wires |  | 6 | Z
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  | 19 | Z
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  | 133 | Z
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  | 198 | Z
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  | 10 | Z
13.49-13.55 | Lostock station | No bases, masts or wires |  | 6 | Z
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | Approx 78 bases in place, no masts, no wires. |  | 152 | M |  | Updated 16th Mar
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  | 6 | Z
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | Approx 60 bases in place, no masts, no wires. |  | 118 | M |  | Updated 16th Mar
17.11-17.17 | Blackrod station | No bases, masts or wires |  | 6 | Z
17.17-19.12 | Blackrod station north end to Adlington station south end | Approx 78 bases in place, no masts, no wires. |  | 155 | M |  | Updated 16th Mar
19.12-19.18 | Adlington station | No bases, masts or wires |  | 6 | Z
19.18-22.17 | Adlington station north end to Chorley station south end | Many scrapes dug, but no bases, no masts, no wires. |  | 239 | M |  | Updated 16th Mar
22.17-22.23 | Chorley station | No bases, masts or wires |  | 6 | Z
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  | 173 | Z
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  | 6 | Z
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  | 69 | Z | [5 empty] | MVch | Mvmiles | Mvmich
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  | 491 | A | [5 empty] | 0 | 0 | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  | 348 | Z | [5 empty] | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  | 6 | Z | [5 empty] | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  | 175 | Z | [5 empty] | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  | 87 | Z | [5 empty] | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  | 466 | Z | [5 empty] | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  | 12 | Z | [5 empty] | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  | 149 | Z | [5 empty] | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  | 6 | Z | [5 empty] | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  | 94 | Z | [5 empty] | 0 | 0 | 0
|  |  | Total | 3857
m.ch | Lostock Junction to Wigan North Western |  |  | Chains | Status
From-To |  |  |  | (Approx) | [6 empty] | MVch | Mvmiles | Mvmich
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  | 143 | Z
1.63-1.69 | Westhoughton station | No bases, masts or wires |  | 6 | Z | [5 empty] | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  | 150 | Z
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  | 30 | Z
4.09-4.15 | Hindley station | No bases, masts or wires |  | 6 | Z
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  | 123 | Z
5.58-5.64 | Ince station | No bases, masts or wires |  | 6 | Z
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  | 50 | Z
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  | A
|  |  | Total | 514
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction |  |  | Chains | Status
From-To |  |  |  | (Approx) | [6 empty] | MVch | Mvmiles | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  | 139 | Z | [5 empty] | 0 | 0 | 0
|  |  | Total | 139
`
Table 2. This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' column M was suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[5 empty] | 2015-03-16 | Change | 2015-03-08 | Change | 2015-03-08
| Key |  |  | Chains | % |  | % |  | %
| A | Fully wired since 1961 or 1974 |  | 491 | 10.89% | 0% | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  | 0 | 0% | 0% | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  | 0 | 0% | 0% | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  | 0 | 0% | 0% | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  | 27 | 0.5987% | 0% | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  | 0 | 0% | 0% | 0% | 0% | 0%
| G | Single wire on one side of tracks |  | 0 | 0% | 0% | 0% | 0% | 0%
| H | Fully masted, no wires |  | 21 | 0.4656% | 0% | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  | 0 | 0% | 0% | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  | 0 | 0% | 0% | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  | 0 | 0% | 0% | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  | 0 | 0% | 0% | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  | 728 | 16.14% | 0% | 16.14% | 0% | 16.14%
| Z | No bases, masts or wires |  | 3243 | 71.91% | 0% | 71.91% | 0% | 71.91%
|  |  | Overall | 4510 | 100% |  | 100% |  | 100%

## 8 Mar 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
m.ch | Manchester Victoria to Blackpool |  |  | Chains | Status
From-To |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  | 8 | H
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  | 13 | H
0.56-0.62 | Salford Central | No bases, masts or wires |  | 6 | Z
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | 26 bases in place, no masts, no wires |  | 64 | M |  | Updated 9th March
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  | 20 | Z
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | No bases, masts or wires |  | 228 | Z
4.54-4.60 | Clifton Station | No bases, masts or wires |  | 6 | Z
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  | 234 | Z
7.54-7.60 | Kearsley Station | No bases, masts or wires |  | 6 | Z
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  | 48 | Z
8.28-8.34 | Kearsley Station | No bases, masts or wires |  | 6 | Z
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  | 49 | Z
9.03-9.09 | Moses Gate station | No bases, masts or wires |  | 6 | Z
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  | 19 | Z
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  | 133 | Z
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  | 198 | Z
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  | 10 | Z
13.49-13.55 | Lostock station | No bases, masts or wires |  | 6 | Z
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | 64 bases in place, no masts, no wires. |  | 152 | M |  | Updated 9th Mar
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  | 6 | Z
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | 33 bases in place, no masts, no wires. |  | 118 | M |  | Updated 9th Mar
17.11-17.17 | Blackrod station | No bases, masts or wires |  | 6 | Z
17.17-19.12 | Blackrod station north end to Adlington station south end | 57 bases in place, no masts, no wires. |  | 155 | M |  | Updated 9th Mar
19.12-19.18 | Adlington station | No bases, masts or wires |  | 6 | Z
19.18-22.17 | Adlington station north end to Chorley station south end | Many scrapes dug, but no bases, no masts, no wires. |  | 239 | M |  | Updated 9th Mar
22.17-22.23 | Chorley station | No bases, masts or wires |  | 6 | Z
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  | 173 | Z
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  | 6 | Z
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  | 69 | Z |  |  |  | MVch | Mvmiles | Mvmich
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  | 491 | A |  |  |  | 0 | 0 | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  | 348 | Z |  |  |  | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  | 6 | Z |  |  |  | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  | 175 | Z |  |  |  | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  | 87 | Z |  |  |  | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  | 466 | Z |  |  |  | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  | 12 | Z |  |  |  | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  | 149 | Z |  |  |  | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  | 6 | Z |  |  |  | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  | 94 | Z |  |  |  | 0 | 0 | 0
|  |  | Total | 3857
m.ch | Lostock Junction to Wigan North Western |  |  | Chains | Status
From-To |  |  |  | (Approx) |  |  |  |  | MVch | Mvmiles | Mvmich
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  | 143 | Z
1.63-1.69 | Westhoughton station | No bases, masts or wires |  | 6 | Z |  |  |  | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  | 150 | Z
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  | 30 | Z
4.09-4.15 | Hindley station | No bases, masts or wires |  | 6 | Z
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  | 123 | Z
5.58-5.64 | Ince station | No bases, masts or wires |  | 6 | Z
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  | 50 | Z
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  | A
|  |  | Total | 514
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction |  |  | Chains | Status
From-To |  |  |  | (Approx) |  |  |  |  | MVch | Mvmiles | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  | 139 | Z |  |  |  | 0 | 0 | 0
|  |  | Total | 139
`
Table 2. This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
NB: the 'Change' column M was suggested by Terry McMenamin of Derby, who also took the trouble to supply a prototype
[5 empty] | 2015-03-08 | Change | 2015-03-01
| Key |  |  | Chains | % |  | %
| A | Fully wired since 1961 or 1974 |  | 491 | 10.89% | 0% | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  | 0 | 0% | 0% | 0%
| C | Major piling, base-building and masting in progress |  | 0 | 0% | 0% | 0%
| D | Fully wired in 2013-5 |  | 0 | 0% | 0% | 0%
| E | Multiple wires over tracks, but not all |  | 27 | 0.5987% | 0% | 0.5987%
| F | Single wire on both sides of tracks |  | 0 | 0% | 0% | 0%
| G | Single wire on one side of tracks |  | 0 | 0% | 0% | 0%
| H | Fully masted, no wires |  | 21 | 0.4656% | 0% | 0.4656%
| I | All bases in place, mostly with masts, no wires |  | 0 | 0% | 0% | 0%
| J | All bases in place, approx half with masts, no wires |  | 0 | 0% | 0% | 0%
| K | All bases in place, some with masts, no wires |  | 0 | 0% | 0% | 0%
| L | All bases in place, no masts, no wires |  | 0 | 0% | 0% | 0%
| M | Some bases in place, no masts, no wires. |  | 728 | 16.14% | 14.72% | 1.419%
| Z | No bases, masts or wires |  | 3243 | 71.91% | -14.72% | 86.63%
|  |  | Overall | 4510 | 100% |  | 100%

## 1 Mar 2015
NW Electrification, Phases 3, 4 and 7
Table 1. This table aims to give a visual representation of progress over time. The colour key is at the foot.
Route data derived from 'Railway Track Diagrams, Book 4, Midlands and North West' 3rd Edition 2013, ISBN 978-9549866-7-4.
m.ch | Manchester Victoria to Blackpool |  |  | Chains | Status
From-To |  |  |  | (Approx)
MVE1 Manchester Victoria to Bolton
0.08-0.35 | Manchester Victoria Station West End to Manchester Victoria West Jct | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  | 27 | E
0.35-0.43 | Manchester Victoria West Jct to Deal Street Jn | Being electrified as part of Phase 2. Appears to be almost fully wired. NR Orangeman expects completion at 'Easter'. |  | 8 | H
0.43-0.56 | Deal Street Jn to Salford Central east end | Fully masted, no wires (NB: 'no wires' needs checking) |  | 13 | H
0.56-0.62 | Salford Central | No bases, masts or wires |  | 6 | Z
0.62-1.46 | Salford Central west end to Windsor Bridge South Junction | 26 mast bases in place |  | 64 | M
1.46-1.66 | Windsor Bridge South Junction to Windsor Bridge North Junction (includes Salfrord Crescent) | No bases, masts or wires |  | 20 | Z
1.66-4.54 | Windsor Bridge North Junction to south end of Clifton station | No bases, masts or wires |  | 228 | Z
4.54-4.60 | Clifton Station | No bases, masts or wires |  | 6 | Z
4.60-7.54 | Clifton Station north end to Kearsley station south end | No bases, masts or wires |  | 234 | Z
7.54-7.60 | Kearsley Station | No bases, masts or wires |  | 6 | Z
7.60-8.28 | Kearsley Station north end to Farnworth Station south end | Major tunnel works planned during 2015 |  | 48 | Z
8.28-8.34 | Kearsley Station | No bases, masts or wires |  | 6 | Z
8.34-9.03 | Kearsley station north end to Moses Gate station south end | No bases, masts or wires |  | 49 | Z
9.03-9.09 | Moses Gate station | No bases, masts or wires |  | 6 | Z
9.09-9.28 | Moses Gate station north end to Moses Gate Jn (ie southern end of the loops) | No bases, masts or wires |  | 19 | Z
9.28-11.01 | Moses Gate Jn to Bullfields (or Moor Lane) Tunnels; includes Bolton station. | Major works planned during 2015 |  | 133 | Z
MVE2 Bolton to Euxton Junction
11.01-13.39 | Bullfields (or Moor Lane) Tunnels to Lostock Jn | No bases, masts or wires |  | 198 | Z
13.39-13.49 | Lostock Jn to Lostock station south end | No bases, masts or wires |  | 10 | Z
13.49-13.55 | Lostock station | No bases, masts or wires |  | 6 | Z
13.55-15.47 | Lostock station north end to Horwich Parkway station south end | No bases, masts or wires |  | 152 | Z
15.47-15.53 | Horwich Parkway station | No bases, masts or wires |  | 6 | Z
15.53-17.11 | Horwich Parkway station north end to Blackrod station south end | No bases, masts or wires |  | 118 | Z
17.11-17.17 | Blackrod station | No bases, masts or wires |  | 6 | Z
17.17-19.12 | Blackrod station north end to Adlington station south end | No bases, masts or wires |  | 155 | Z
19.12-19.18 | Adlington station | No bases, masts or wires |  | 6 | Z
19.18-22.17 | Adlington station north end to Chorley station south end | No bases, masts or wires |  | 239 | Z
22.17-22.23 | Chorley station | No bases, masts or wires |  | 6 | Z | No bases, masts or wires
22.23-24.36 | Chorley station north end to Buckshaw Parkway station south end | No bases, masts or wires |  | 173 | Z | No bases, masts or wires
24.36-24.42 | Buckshaw Parkway station | No bases, masts or wires |  | 6 | Z
24.42-25.31 | Buckshaw Parkway station north end to Euxton Jn | No bases, masts or wires |  | 69 | Z |  |  | MVch | Mvmiles | Mvmich
CGJ5 Euxton Junction to Preston (WCML)
25.31-31.42 | Euxton Jn to Preston Power Box Sidings | Fully wired since 1974 |  | 491 | A |  |  | 0 | 0 | 0
PBN Preston to Blackpool North
31.42-35.70 | Preston Power Box Sidings to Salwick station south end | No bases, masts or wires |  | 348 | Z |  |  | 0 | 0 | 0
35.70-35.76 | Salwick station | No bases, masts or wires |  | 6 | Z |  |  | 0 | 0 | 0
35.76-38.11 | Salwick station north end to Kirkham South Jn | No bases, masts or wires |  | 175 | Z |  |  | 0 | 0 | 0
38.11-39.18 | Kirkham South Jn to Kirkham North Jn | No bases, masts or wires |  | 87 | Z |  |  | 0 | 0 | 0
39.18-45.04 | Kirkham North Jn to Poulton-le-Fylde station south end | No bases, masts or wires |  | 466 | Z |  |  | 0 | 0 | 0
45.04-45.16 | Poulton-le-Fylde station south end to Poulton-le-Fylde Jn (includes Poulton-le-F Station) | No bases, masts or wires |  | 12 | Z |  |  | 0 | 0 | 0
45.16-47.50 | Poulton-le-Fylde Jn-Layton station east end | No bases, masts or wires |  | 149 | Z |  |  | 0 | 0 | 0
47.50-47.56 | Layton station | No bases, masts or wires |  | 6 | Z |  |  | 0 | 0 | 0
47.56-48.25 | Layton station west end to Blackpool North bufferstops | No bases, masts or wires |  | 94 | Z |  |  | 0 | 0 | 0
|  |  | Total | 3857
m.ch | Lostock Junction to Wigan North Western |  |  | Chains | Status
From-To |  |  |  | (Approx) |  |  |  | MVch | Mvmiles | Mvmich
LCN Lostock Junction to Crow Nest Junction
0.00-1.63 | Lostock Jn to Westhoughton station east end | No bases, masts or wires |  | 143 | Z
1.63-1.69 | Westhoughton station | No bases, masts or wires |  | 6 | Z |  |  | 0 | 0 | 0
1.69-3.59 | Westhoughton station west end to Crow Nest Jn | No bases, masts or wires |  | 150 | Z
WBS2 Crow Nest Junction to Wigan North Western (WCML)
3.59-4.09 | Crow Nest Jn to Hindley station east end | No bases, masts or wires |  | 30 | Z
4.09-4.15 | Hindley station | No bases, masts or wires |  | 6 | Z
4.15-5.58 | Hindley station west end to Ince station east end | No bases, masts or wires |  | 123 | Z
5.58-5.64 | Ince station | No bases, masts or wires |  | 6 | Z
5.64-6.34 | Ince station west end to Wigan Station Jn | No bases, masts or wires |  | 50 | Z
| Wigan Station Jn into Wigan NW station | Fully wired since 1974 |  |  | A
|  |  | Total | 514
m.ch | Ordsall Lane Junction to Windsor Bridge South Junction |  |  | Chains | Status
From-To |  |  |  | (Approx) |  |  |  | MVch | Mvmiles | Mvmich
OLW Ordsall Lane Junction to Windsor Bridge South Junction
0.0-1.59 | Ordsall Lane Jn to Windsor Bridge South Jn ('Windsor Link') | No bases, masts or wires except for 'lead in' wire at southern end, c100 yds long |  | 139 | Z |  |  | 0 | 0 | 0
|  |  | Total | 139
`
Table 2. This table serves both as the key for the colour coding and to summarise the lengths and % of progress.
2015-03-01
| Key |  |  | Chains | %
| A | Fully wired since 1961 or 1974 |  | 491 | 10.89%
| B | Interleaved 1961/74 wires and new kit under construction |  | 0 | 0%
| C | Major piling, base-building and masting in progress |  | 0 | 0%
| D | Fully wired in 2013-5 |  | 0 | 0%
| E | Multiple wires over tracks, but not all |  | 27 | 0.5987%
| F | Single wire on both sides of tracks |  | 0 | 0%
| G | Single wire on one side of tracks |  | 0 | 0%
| H | Fully masted, no wires |  | 21 | 0.4656%
| I | All bases in place, mostly with masts, no wires |  | 0 | 0%
| J | All bases in place, approx half with masts, no wires |  | 0 | 0%
| K | All bases in place, some with masts, no wires |  | 0 | 0%
| L | All bases in place, no masts, no wires |  | 0 | 0%
| M | Some bases in place, no masts, no wires. |  | 64 | 1.419%
| Z | No bases, masts or wires |  | 3907 | 86.63%
|  |  | Overall | 4510 | 100%

## Railway Links
Subject Matter | Login | Password
Greengauge21 |  |  | http://www.greengauge21.net/
HS2 Debate 2014 04 28 |  |  | http://www.parliament.uk/business/publications/hansard/commons/todays-commons-debates/read/unknown/307/2014-04-28
North Rail Consultation 2014 |  |  | https://www.gov.uk/government/consultations/future-of-northern-and-transpennine-express-rail-franchises
Real Time Signalling, Huyton Area | livesig | guest | http://www.charlwoodhouse.co.uk/rail/livesig | guest | livesig
NR Lines and Codes (ELRs) |  |  | http://www.networkrail.co.uk/browse%20documents/baseline%20capability/electrification%20type%20and%20miles/electrified%20track%20capability.pdf
Planning Rainhill |  |  | http://llpgport.oltps.sthelens.gov.uk/portal/servlets/ApplicationSearchServlet?PKID=101342
Flickr NW Electrification 2013-4 |  |  | https://www.flickr.com/photos/127646831@N03/sets/72157648494725811/
HS2 alternatives considered |  |  | https://www.gov.uk/government/publications/rail-alternatives-to-hs2
Railway Signs Explanations |  |  | http://www.railsigns.uk/info/other1/other1.html
Modern Railways |  |  | http://www.modern-railways.com/
Railnews |  |  | http://www.railnews.co.uk/
Railway Magazine |  |  | http://www.railwaymagazine.co.uk/
Engineers Line References (ELRs) |  |  | http://www.railwaycodes.org.uk/index.shtml
NW-sparks (NW Electrification) |  |  | http://nw-sparks.co.uk/
Planning Earlestown Station |  |  | http://llpgport.oltps.sthelens.gov.uk/portal/servlets/ApplicationSearchServlet?PKID=100855
Crossrail |  |  | http://www.crossrail.co.uk/
Northern Electrics |  |  | http://www.northernrail.org/northern/electric-trains
NR WTT |  |  | http://www.networkrail.co.uk/browsedirectory.aspx?root=&dir=%5cTimetables%5cWorking%20Timetable%20(WTT)
Signalling Record Society |  |  | http://www.s-r-s.org.uk/RailRef/ref-nw.php#684
OXERA Report for RDG |  |  | http://www.oxera.com/getmedia/802a4979-8371-4063-ad24-8a81ed6c8f82/Contribution-of-rail-to-the-UK-economy-140714.pdf.aspx?ext=.pdf
abc Railway Guide |  |  | http://abcrailwayguide.co.uk/
Railway Maps |  |  | http://www.railmaponline.com/UKIEMap.php
General Modern Railways |  |  | www.mnevattuktrains.co.uk